## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Srinidhi M | 2026-09-02 | chroma-hnswlib failed to build on Python 3.12 (no prebuilt Windows wheel) | Sprint 1 | Srinidhi M | Standards | Recreated venv using Python 3.11, where prebuilt wheels exist for chroma-hnswlib | 2026-02-09 | Closed | Requires chromadb — root-caused to Python version, not the library; resolved by switching venv Python version rather than avoiding the library
2 | Srinidhi M | 2026-09-03 | CSV file containing smart quotes/non-UTF-8 characters raised UnicodeDecodeError during ingestion | Sprint 1 | Srinidhi M | Maintainability | Opened files with encoding='utf-8', errors='ignore' so malformed characters are skipped instead of crashing the loader | 2026-03-09 | Closed | Low-risk fix; may silently drop a few odd characters, acceptable for this milestone
3 | Srinidhi M | 2026-09-15 | app/config.py and app/rag/vector_store.py edits for Milestone 2 (Gemini/OpenAI config, get_chunks_by_source, get_document_text, list_sources) did not persist to the repo, causing ImportError/ModuleNotFoundError when running agent tests | Sprint 2 | Srinidhi M | Standards | Re-applied full file contents for both files and verified imports resolved | 2026-09-15 | Closed | Root cause was incomplete file save/sync, not a logic defect; fixed by full-file replacement instead of partial edits
4 | Srinidhi M | 2026-09-16 | pip install failed with dependency conflict: google-genai requires httpx>=0.28.1 but requirements.txt pinned httpx==0.27.2 for chromadb/tests | Sprint 2 | Srinidhi M | Standards | Loosened httpx pin to >=0.28.1, confirmed chromadb==0.5.5 still installs cleanly | 2026-09-16 | Closed | Low-risk fix; resolved by version range relaxation rather than pinning a specific compatible version
5 | Srinidhi M | 2026-09-17 | OpenAI agent calls failed with 429 insufficient_quota — API key had no funded billing credits | Sprint 2 | Srinidhi M | Maintainability | Evaluated switching LLM provider; moved to Google Gemini free tier to avoid billing dependency | 2026-09-17 | Closed | Not a code defect; free-tier LLM providers were preferred for a student project to avoid recurring cost
6 | Srinidhi M | 2026-09-17 | Gemini calls failed with 404 NOT_FOUND (gemini-2.5-flash no longer available to new users), then 429 RESOURCE_EXHAUSTED (gemini-3.6-flash limited to 20 requests/day on free tier) | Sprint 2 | Srinidhi M | Maintainability | Migrated LLM provider again, this time to Groq (llama-3.3-70b-versatile) for a more stable free tier | 2026-09-17 | Closed | Cloud LLM model availability/quotas changed twice during development; mitigated by keeping provider logic isolated to a single llm_client.py module
7 | Srinidhi M | 2026-09-18 | openai SDK raised Client.__init__() got an unexpected keyword argument 'proxies' after reinstalling dependencies for Groq migration | Sprint 2 | Srinidhi M | Standards | Reverted httpx pin to ==0.27.2 (compatible with openai==1.51.0) since google-genai was no longer a dependency | 2026-09-18 | Closed | Recurrence of the httpx conflict in reverse direction; resolved by matching pin to whichever LLM SDK is active
8 | Srinidhi M | 2026-09-18 | Groq agent calls failed with 404 model_not_found — llama-3.3-70b-versatile deprecated by Groq | Sprint 2 | Srinidhi M | Maintainability | Switched model to Groq's recommended replacement, openai/gpt-oss-120b | 2026-09-18 | Closed | Final stable configuration; all 3 agents validated successfully across PDF/DOCX/CSV/TXT sample documents after this fix
9 | Srinidhi M | 2026-09-29 | Grounded Assistant Chat drawer returned HTTP 500 when document citation snippet contained single quotes | Sprint 3 | Srinidhi M | Maintainability | Escaped quote strings in citation payload formatting before rendering citation chips | 2026-09-29 | Closed | Resolved JSON parsing issue in AssistantPanel response renderer
10 | Srinidhi M | 2026-10-06 | Single-line doc.text() in jsPDF caused text to overflow right margin and cut off risk table columns | Sprint 3 | Srinidhi M | Logical | Refactored text rendering using doc.splitTextToSize() and dynamic cell height calculation | 2026-10-06 | Closed | Multi-page PDF export renders formatted tables without text truncation
11 | Srinidhi M | 2026-10-06 | Switching active project folder did not update Document Library state, causing data leakage | Sprint 3 | Srinidhi M | Logical | Upgraded ProjectContext to maintain isolated projectStores mapped by project ID | 2026-10-06 | Closed | Isolates documents, risks, and chat history strictly per project workspace
12 | Srinidhi M | 2026-10-06 | What-If simulation health score slider allowed negative values resulting in invalid negative health index | Sprint 3 | Srinidhi M | User Interface | Added Math.max(0, Math.min(100, score)) boundary bounds in calculation engine | 2026-10-06 | Closed | Clamped simulation health score range between 0 and 100
13 | Srinidhi M | 2026-10-06 | Document ingestion completed without populating Document Library, Risks matrix, or Deliverables | Sprint 3 | Srinidhi M | Standards | Added completion handler callback in UploadIngestion.tsx to update active context state | 2026-10-06 | Closed | State synchronization populates documents and risks upon pipeline completion
14 | Srinidhi M | 2026-10-06 | Legacy PostCSS utility classes conflicted with Vite v8 @tailwindcss/vite plugin setup | Sprint 3 | Srinidhi M | User Interface | Replaced legacy config with Tailwind v4 @import "tailwindcss"; and root CSS variables | 2026-10-06 | Closed | Verified clean production bundle build (npm run build) in 801ms
15 | Srinidhi M | 2026-10-07 | Executive PDF download filename crashed when project folder name contained spaces | Sprint 3 | Srinidhi M | Maintainability | Applied .toLowerCase().replace(/\s+/g, '_') sanitization to output filename string | 2026-10-07 | Closed | Ensures valid cross-platform PDF download file naming

## Sheet2
Logical
User Interface
Maintainability
Standards
Others