CAMPUSCARE – SPRINT 4 TEAM MEETING NOTES

Meeting Date: 14 September 2026

Meeting Type: Weekly Project Meeting

Attendees: Aarav, Meera, Rohan, Nisha

1. CURRENT PROGRESS

The authentication module has been completed and basic login testing has passed.

The student support-request form has been implemented on the frontend.

The backend API for creating support requests is available, but the API documentation has not yet been finalized.

The administrator dashboard is approximately 70% complete.

The AI assistance module has not yet been integrated because the cloud LLM API credentials have not been finalized.

2. ISSUES DISCUSSED

Issue 1 – AI API Access

Rohan reported that the team has not yet received the final API credentials for the cloud LLM service.

This is blocking implementation and testing of the AI assistance module.

Decision pending: The team needs to decide which cloud LLM provider and model will be used for the final deployment.

Assigned to: Rohan

Target date: 16 September 2026

Issue 2 – Database Schema Change

The support-request table currently does not contain a priority field.

The team agreed that priority is required for administrator request management.

Aarav will add the priority field and update the API models.

This change may require corresponding frontend changes.

Assigned to: Aarav

Target date: 15 September 2026

Issue 3 – Dashboard API Dependency

Meera cannot complete the administrator dashboard statistics because the analytics API is not available yet.

Aarav needs to provide the initial analytics endpoint before the dashboard can be completed.

Assigned to: Aarav

Target date: 17 September 2026

Issue 4 – Email Notification Service

The email notification component has not been tested because the SMTP configuration is incomplete.

Nisha requested a test email account or approved SMTP credentials.

Assigned to: Nisha

Target date: 18 September 2026

3. RISKS DISCUSSED

Risk 1: Delay in obtaining the cloud LLM API credentials may push the AI integration beyond Week 6. Risk Level: High

Risk 2: The database schema change may require modifications to already completed frontend components. Risk Level: Medium

Risk 3: The analytics API dependency may delay completion of the administrator dashboard. Risk Level: Medium

Risk 4: Incomplete SMTP configuration may prevent end-to-end testing of email notifications. Risk Level: Medium

4. PENDING DECISIONS

1. Final cloud LLM provider and model selection.

2. Whether request priority should contain three levels or four levels.

3. Whether email notifications should be enabled for all status changes or only important status changes.

5. ACTION ITEMS

1. Aarav – Update database schema with request priority field – Due 15 September.

2. Rohan – Finalize cloud LLM API access – Due 16 September.

3. Aarav – Provide analytics API endpoint – Due 17 September.

4. Nisha – Complete SMTP test configuration – Due 18 September.

5. Meera – Complete administrator dashboard after analytics API availability – Due 19 September.

6. OVERALL STATUS

The core authentication and request creation functionality is progressing as planned.

However, AI integration, analytics, and notification functionality currently have unresolved dependencies.

The team should prioritize resolving external API access and backend API dependencies before the next sprint review.